## ReadMe
Ops Manager Daily Tracker
How to use this workbook (2-3 minutes at end of each day):
1. DailyHours tab - add one row per working day: Date, Start, Finish, Break minutes. Hours Worked calculates itself.
2. TaskLog tab - add one row per task per day, straight from your End of Day report: the task, what 'done' means, estimated vs actual hours, status, evidence link, and the reason + new date if it slipped.
3. MonthlySummary tab - nothing to type. It accumulates hours and achievements per month and cumulatively on its own.
Legend - which cells to edit:
BLUE text = cells you type into (the example rows show the expected format - overwrite them with your first real day).
Black cells = formulas. Do not type over them.
Both log tabs have formulas pre-filled down to row 500 - just keep adding rows within that range.
Rules that make the numbers mean something:
Every task gets an estimate before the day starts (nearest 0.5 hr) and an actual at end of day.
Status 'Done' is only for finished, checkable outcomes with evidence - it is what MonthlySummary counts as achieved.
Anything not Done keeps a one-sentence reason and a new committed date in the 'If delayed' column.
Companion document: OPS-MANAGER-DAILY-REPORTING.md (start-of-day, end-of-day and break-handover report templates that feed this file).

## DailyHours
Date | Day | Start | Finish | Break (mins) | Hours Worked | Month
2026-08-24 | Mon | 8:30 | 17:00 | 30 | 8 | 2026-08

## TaskLog
Date | Task | Done means (checkable outcome) | Est Hrs | Actual Hrs | Variance (hrs) | Status | Evidence / link | If delayed: why + new date | Month
2026-08-24 | Onboarding email sequence | All 5 emails drafted and loaded into CRM, test send passed | 3 | 3.5 | 0.5 | Done | CRM > Sequences > 'New Client Onboarding' |  | 2026-08
2026-08-24 | August invoice run | All client invoices issued in Xero and log updated | 1.5 | 1 | -0.5 | Done | Xero invoice list 24-Aug |  | 2026-08
2026-08-24 | Supplier contract review | Redlines returned to supplier with cover note | 2 | 1 | -1 | In Progress |  | Waiting on pricing schedule from supplier - chased 24-Aug, will complete 25-Aug | 2026-08

## MonthlySummary
Month key | Month | Hours Worked | Days Worked | Avg Hrs/Day | Tasks Logged | Tasks Completed | Completion % | Est Hrs (tasks) | Actual Hrs (tasks) | Cumulative Hours | Cumulative Tasks Completed
2026-08 | Aug-26 | 8 | 1 | 8 | 3 | 2 | 66.67% | 6.5 | 5.5 | 8 | 2
2026-09 | Sep-26 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 8 | 2
2026-10 | Oct-26 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 8 | 2
2026-11 | Nov-26 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 8 | 2
2026-12 | Dec-26 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 8 | 2
2027-01 | Jan-27 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 8 | 2
2027-02 | Feb-27 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 8 | 2
2027-03 | Mar-27 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 8 | 2
2027-04 | Apr-27 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 8 | 2
2027-05 | May-27 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 8 | 2
2027-06 | Jun-27 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 8 | 2
2027-07 | Jul-27 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 8 | 2
2027-08 | Aug-27 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 8 | 2
2027-09 | Sep-27 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 8 | 2
2027-10 | Oct-27 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 8 | 2
2027-11 | Nov-27 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 8 | 2
2027-12 | Dec-27 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 8 | 2
| TOTAL | 8 | 1 |  | 3 | 2 | 66.67% | 6.5 | 5.5
All figures calculate automatically from DailyHours and TaskLog (rows 2-500). 'Tasks Completed' counts TaskLog rows with Status = Done. Months pre-built Aug-2026 to Dec-2027; copy the last row down to extend.